## Group A Checklist
TX COMMUNITY RESILIENCY PROGRAM (CRP) CONSTRUCTION PROJECT - Group A Documents Checklist (before 1st Draw) Effective 1/31/2023
All Group A documents must be received by TDHCA before submitting 1st Draw
Subrecipient:____________________________________________ Revised Date: ____________________
Group A | Category | Required Documents | Sample Documents | Submitted (Y/N) | Notes | Instructions | How to Submit
| Civil Rights Policies | Fair Housing Policy | A1015 |  |  | 1. Adopt any Civil Rights Policies not currently in effect 2. Pass Resolution to adopt/affirm/reaffirm the Civil Rights Policies listed are effective for the Grant Recipient (TDA Form A1014) 3. Per submission, the Department prefers all documents submitted as one PDF file 4. An updated CRP Documents Checklist must be submitted with each submission | CRP Document Submission Portal
|  | Fair Housing Activities: Month Proclamation (A1007), Public Service Announcement (A1009) | A1007 |  | Best practice: Plan at least one activity within the contract term to Affirmatively Further Fair Housing
A1009
|  | Section 504 Self Evaluation | A1006 |  | Required if the subrecipient has 15 or more employees
|  | Section 504 Policy and Grievance Procedure | A1004 |  | Required if the subrecipient has 15 or more employees
|  | Excessive Force Policy | A1003
|  | Non-Discrimination Notices | A1005 |  | Notice 1 (15 or more employees) Must identify Civil Rights Officer; Notice 2 (all) Citizen Participation Plan & Grievance Procedures (A1013) - Post Notice after adoption of plan/procedure
|  | Citizen Participation Plan and Complaint Procedures | A1013 |  | In addition to public hearing requirements, publish Notice (Notice 2) to make citizens aware of location/hours in which they may obtain copy of grievance procedures and address, phone, and time to file complaints
|  | Code of Conduct | A1002-22
|  | Limited English Proficiency Plan | HUD link |  | Follow HUD LEP guidance provided in link
| Section 3 | Section 3 Area Map | A1021
| Labor Standards (Davis-Bacon) | Appointment of Labor Standards Officer | DB01
| Civil Rights & Section 3 Resolution and Responsibilities | Resolution adopting/reaffirming Community Policies | A1014 |  | Adopting new policies and re-affirming existing policies can be completed in the same resolution. All required resolutions, ordinances and/or policies regarding civil rights, equal opportunity, and citizen participation must be in effect throughout the CRP grant agreement period
| Other | Photos of Bldg or Lot | n/a
|  | Acquisition Report Form | Form

## Group B Checklist
TX COMMUNITY RESILIENCY PROGRAM (CRP) CONSTRUCTION PROJECT - Group B Documents Checklist (before 1st Construction Draw) Effective 4/18/2024
All Group B documents must be received by TDHCA before submitting 1st Construction Draw
Subrecipient:____________________________________________ Revised Date: ____________________
| Form Category | Forms & Required Documentation | Document # | Submitted/Completed (Y/N) | Notes | Instructions | How to Submit
Group B | Section 3 | Section 3 Presentation | Sample PPT |  | Section 3 Presentation Documentation: meeting notices posted, agenda and sign-in, or items to that effect *Presentation / open public meeting must occur prior to bid | Submit Section 3 Presentation documentation | CRP Document Submission Portal
| Labor Standards (Davis-Bacon) | Wage Determination Form | DB02 |  | Form DB02 must be submitted to TDHCA and approved prior to bid | Submit form DB02 prior to bid
|  | 10 Day Call Form | DB03 |  | Form DB03 must be submitted to TDHCA and approved prior to bid | Submit form DB03 prior to bid
|  | Pre-Construction Conference Conducted? | n/a |  | (Y) if Preconstruction Conference completed | Indicate whether the Pre-Construction Conference has been held (Y/N), and the date of the conference
|  | Notice to Proceed (TDHCA) | n/a |  | (Y) if Notice to Proceed has been issued by TDHCA | Indicate whether the Notice to Proceed has been issued by TDHCA (Y/N) and the date issued
|  | Notice to Proceed (Local) | n/a |  | (Y) if Notice to Proceed (Local) has been submitted to TDHCA | Submit the local Notice to Proceed issued to the Construction Contractor
|  | On-Site Posting Requirements (photo) | n/a |  | The following items must be posted on a notice board in a visible location at the job-site: -Davis-Bacon poster -Davis-Bacon prevailing wage rates -Executive Order 11246 ("Know Your Rights" Equal Employment Opportunity poster) -Worker's Compensation Notices | Submit photo(s) of required items posted on-site
| Other | SAM.gov Construction Contractor Clearance | SAM.gov |  | The LSO must verify prior to awarding and executing the construction contract that all prime contractors, including the principal owner(s) and their subcontractors, are not listed as “debarred” in the System for Award Management (SAM) SAM.gov. | Submit support documentation verifying contractor clearance in SAM.gov
|  | CRP Project Temporary Signage | link to workshop slides |  | Signage Requirements: - Placed in a prominent, visible area that is not blocked or obscured - Constructed of durable materials - Minimum size of 4' x 8' - For sample signage language, please refer to the CRP Public Facilities Implementation Workshop slides (Slide 29) | Submit a photo of the temporary project signage
|  | Special Conditions (Prior to Construction) | n/a |  | Required Special Conditions will be included in the CRP contract | Submit if applicable
*Additional CRP forms & documents can be found on the CRP Webage |  |  | CRP Webpage

## Group C Checklist
TX COMMUNITY RESILIENCY PROGRAM (CRP) CONSTRUCTION PROJECT - Group C Documents Checklist (before Final Draw) Effective DATE - 4/18/2024
All Group C documents must be received by TDHCA prior to Final Draw
Subrecipient:____________________________________________ Revised Date: ____________________
| Form Category | Forms & Required Documentation | Document # / Name | Submitted (Y/N) | Notes | Instructions | How to Submit
Group C | Completion Report | CRP Program Completion Report (PCR) | n/a |  | TDHCA will email a Subrecipient-specific PCR to be completed by Subrecipient before final draw | Submit all documents through the CRP Document Submission Portal | CRP Documents Submission Portal
| Building | Final inspection, including 2010 ADA Standards for Accessible Design | n/a |  | CRP Contract Special Conditions - Subrecipient shall comply with the 2010 ADA Standards for Accessible Design, except for certain provisions identified in "Nondiscrimination on the Basis of Disability in Federally Assisted Programs and Activities; Instructions for use of alternative accessibility standard," 79 Federal Register 29671 (May 23, 2014), pp. 29671-29676, for purposes of complying with Section 504 of the Rehabilitation Act of 1973 and HUD's Section 504 regulations at 24 CFR Part 8.
|  | Certificate of Occupancy (COO), or equivalent | n/a |  | * Required for COCC/DB12 CRP Contract Special Conditions - Subrecipient shall submit to the Department the Certification of Occupancy prior to submitting the final retaining payment
| Hearings | Final Public Hearing Notice | n/a |  | Support documentation
|  | Final Public Hearing Agenda/Minutes | n/a |  | Support documentation
| Davis-Bacon | Certificate of Construction Completion (COCC) | DB12 |  | * liquidated damages * warranties * Certificate of Occupancy (COO) or equivalent * support documentation - all construction invoices fully paid
|  | Final Wage Compliance Report | DB13
| Section 3 | Section 3 Cumulative Report | S302

## Group D Checklist
TX COMMUNITY RESILIENCY PROGRAM (CRP) CONSTRUCTION PROJECT - Group D Documents Checklist (post Contract) Effective DATE - 4/18/2024
Group D documents must be received by TDHCA annually until the LURA expires
Subrecipient:____________________________________________ Revised Date: ____________________
| Form Category | Forms & Required Documentation | Document # | Submitted (Y/N) | Notes | Instructions | How to Submit
Group D | LURA | Annual LURA Certification | n/a |  | CRP Contract Special Conditions - Subrecipient shall submit a report detailing the services and/or functions of the facility developed with Contract funds. The initial report shall be submitted by December 31st of the year in which this Contract is closed and shall continue to be submitted annually for five (5) years or any year in which the Use Agreement has been extended. In the final year, Subrecipient must request to have the Use Agreement removed from the Property. The certification must be signed by the owner or a representative with full authority to legally bind the ownership entity. If the certification is signed by anyone other than the person who signed the LURA, evidence of signature authority must be provided. | Submit certification through the CRP Document Submission Portal | CRP Documents Submission Portal